## BarkMate
PROJECT TITLE | PRO1000
PROJECT MANAGER | Andreas
COMPANY NAME | BarkMate
DATE | 2024-01-16
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Start
1.1 | Definere Prosjekt | Andreas | 2024-01-16 | 2024-02-02 | 17 | 100%
1.2 | Definere SWOT | Jostein | 2024-01-16 | 2024-01-20 | 4 | 100%
1.3 | Produkt Backlog | Marcus | 2024-01-16 | 2024-02-02 | 17 | 100%
1.4 | Definere Prosjekt | Andreas | 2024-01-16 | 2024-02-02 | 17 | 100%
2 | Planlegging
2.1 | Sprint 1 | Jostein | 2024-01-24 | 2024-02-02 | 9 | 100%
2.1.1 | WBS | Marcus | 2024-01-29 | 2024-02-02 | 4 | 100%
2.1.2 | Gnatt Chatt | Andreas | 2024-02-02 | 2024-02-03 | 1 | 100%
2.1.3 | Levere Milestone 1 | ALL | 2024-02-04 | 2024-02-05 | 1 | 100%
3 | Utførelse
3.1 | Sprint 2 | Marcus | 2024-02-27 | 2024-03-04 | 6 | 100%
3.1.1 | Brukergrensesnittet | Andreas | 2024-02-28 | 2024-02-29 | 1 | 100%
3.1.2 | Prototyppe 1 | Jostein | 2024-02-29 | 2024-02-29 |  | 100%
3.1.3 | Risikovurdering | Andreas | 30.02.2024 | 30.02.2024 |  | 100%
3.1.4 | Levere Milestone 2 | Andreas | 2024-03-01 | 2024-03-01 |  | 100%
3.1.5 | Prototype 2 | ALL | 2024-03-01 | 2024-03-04 |  | 100%
3.2 | Sprint 3 | ALL | 2024-03-22 | 2024-04-02 |  | 100%
3.2.1 | Prototype 3 | Andreas | 2024-03-22 | 2024-03-31 |  | 100%
3.2.2 | Test fase | Jostein | 2024-03-22 | 2024-03-29 |  | 100%
3.2.3 | Brukergrensersnitt/Universell Utforming | Jostein | 2024-03-29 | 2024-04-02 |  | 100%
3.2.4 | Lever Milestone 3 | Jostein | 2024-04-02 | 2024-04-03 | 1 | 100%
4. | Controll
4.1 | Sprint 4 | ALL | 2024-04-11 | 2024-04-23 | 12 | 100%
4.1.1 | Brukergrensensnitt V2 | Andreas | 2024-04-11 | 2024-04-20 |  | 100%
4.1.2 | Oppdatere WBS/Gnatt Chart/GitHub | Andreas | 2024-04-21 | 2024-04-21 |  | 100%
4.1.3 | Fremstille Produkt | Jostein | 2024-04-22 | 2024-04-22 |  | 100%
4.1.4 | Oppdatere prosjekt status | Jostein | 2024-04-22 | 2024-04-23 | 1 | 100%
5 | Sluttprosess
5.1 | Lever Prosjekt | ALL | 2024-04-25 | 2024-04-25 |  | 100%