## Blank
SIMPLE GANTT CHART TEMPLATE
PROJECT TITLE | PRO1000
PROJECT MANAGER | Andreas
COMPANY NAME | BarkMate
DATE | 2024-01-16
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Initsiajson
1.1 | Definere Prosjekt | Andreas | 2024-01-15 | 2024-01-15 |  | 100%
1.1.1 | Identifisere involverte | Jostein |  |  |  | 100%
1.2 | SWOT | Marcus |  |  |  | 40%
1.3 | Produkt Backlog | Thomas |  |  |  | 100%
1.4 | Oppbygging Prosjekt Kart | Andreas |  | 2024-01-22 | 45313 | 100%
1.5 | Definere Prosjekt kriterier | Jostein |  |  |  | 100%
2 | Planlegging
2.1 | Gantt Chart | Marcus |  |  |  | 100%
2.2 | Milestone 1 | Thomas |  | 01.29.24 | #VALUE! | 100%
2.4 | Risiko Vurdering | Andreas |  |  |  | 30%
3 | Utførelse
3.1 | Prototype Nr 1 | Jostein |  |  |  | 0%
3.2 | Milestone 2 | Marcus |  | 2024-03-03 | 45354 | 0%
3.2.1 | Prototype Nr 2 | Thomas |  |  |  | 0%
3.2.2 | Produkttype Nr 3 | Andreas |  |  |  | 0%
3.3 | Test Fase | Jostein |  |  |  | 0%
3.3.1 | Go Live | Marcus |  |  |  | 0%
4 | Kontroll
4.1 | Prosjekt Ledelses Evaluering | Thomas |  | 2024-03-18 | 45369 | 0%
4.2 | Prosjekt status møte | Andreas |  |  |  | 0%
4.3 | Kommunikasjons Tabell | Jostein |  |  |  | 0%

## Example
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME | BarkMate
DATE | 2024-01-16
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Initsiajson
1.1 | Definere Prosjekt | Andreas | 2023-03-12 | 2023-03-15 | 3 | 100%
1.1.1 | Identifisere involverte | Jostein | 2023-03-15 | 2023-03-16 | 1 | 100%
1.2 | SWOT | Thomas | 2023-03-15 | 2023-03-21 | 6 | 100%
1.3 | Produkt Backlog | Marcus | 2023-03-16 | 2023-03-22 | 6 | 100%
1.4 | Oppbygging Prosjekt Kart | Andreas | 2023-03-17 | 2023-03-22 | 5 | 100%
1.5 | Definere Prosjekt kriterier | Josteim | 2023-03-18 | 2023-03-22 | 4 | 100%
2 | Planlegging
2.1 | Bygge opp prosjektplan | Thomas | 2023-03-24 | 2023-03-28 | 4 | 90%
2.2 | Gantt Chart | Marcus | 2023-03-29 | 2023-04-02 | 4 | 30%
2.3 | Milestone 1 | Andreas |  |  |  | 60%
2. | Markeds Undersøkelser | Josteim |  |  |  | 0%
2.4 | Risiko Vurdering | Thomas |  |  |  | 0%
3 | Utførelse
3.1 | Prototype Nr 1 | Marcus |  |  |  | 0%
3.2 | Prototypr Nr 2 | Andreas |  |  |  | 0%
3.2.1 | Milestone 2 | Jostein |  |  |  | 0%
3.2.2 | Produkttype Nr 3 | Thomas |  |  |  | 0%
3.3 | Test Fase | Pete S |  |  |  | 0%
3.3.1 | Go Live | Malik M |  |  |  | 0%
4 | Kontroll
4.1 | Prosjekt Ledelses Evaluering | Steve L |  |  |  | 0%
4.2 | Prosjekt status møte | Allen W |  |  |  | 0%
4.3 | Kommunikasjons Tabell | Malik M |  |  |  | 0%