## BarkMate
PROJECT TITLE | PRO1000
PROJECT MANAGER | Andreas
COMPANY NAME | BarkMate
DATE | 2024-01-16
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Start
1.1 | Prosjekt planlegging | Andreas | 2024-01-16 | 2024-02-02 | 17 | 100%
1.2 | Analyser | Jostein | 2024-01-16 | 2024-01-20 | 4 | 100%
1.3 | Produkt Backlog | Marcus | 2024-01-16 | 2024-02-02 | 17 | 100%
1.4 | Pre-study | Marcus | 2024-01-18 | 2024-02-01 | 14 | 100%
2 | Sprint 1 | Jostein | 2024-01-24 | 2024-02-02 | 9 | 100%
2.1 | Sprint planlegging | Andreas | 2024-01-24 | 2024-01-24 |  | 100%
2.2 | WBS | Thomas | 2024-01-29 | 2024-02-02 | 4 | 100%
2.3 | Gnatt Chratt | Andreas | 2024-02-02 | 2024-02-03 | 1 | 100%
2.4 | Project sucsess criteria | Jostein | 2024-02-01 | 2024-02-03 | 2 | 100%
2.5 | Prosjektskisse | Andreas | 2024-02-02 | 2024-02-03 | 1 | 100%
2.6 | Levere Milestone 1 | ALL | 2024-02-04 | 2024-02-05 | 1 | 100%
2.7 | Sprint gjennomgangsmøte | Andreas | 2024-02-01 | 2024-02-01 |  | 100%
2.8 | Sprint retrospektmøte | Andreas | 2024-02-02 | 2024-02-02 |  | 100%
3 | Sprint 2 | Marcus | 2024-02-27 | 2024-03-04 | 6 | 100%
3.1 | Sprint planlegging | Andreas | 2024-02-27 | 2024-02-27 |  | 100%
3.2 | Brukergrensesnittet | Andreas | 2024-02-28 | 2024-02-29 | 1 | 100%
3.3 | Prototyppe 1 | Jostein | 2024-02-29 | 2024-02-29 |  | 100%
3.4 | Risikoplan | Andreas | 30.02.2024 | 30.02.2024 |  | 100%
3.5 | Prototype 2 | Andreas | 2024-03-01 | 2024-03-01 |  | 100%
3.6 | Levere Milestone 2 | ALL | 2024-03-01 | 2024-03-04 |  | 100%
3.7 | Presentasjon 1 | ALL | 2024-03-11 | 2024-03-11 |  | 100%
3.8 | Sprint gjennomgangsmøte | Andreas | 2024-03-03 | 2024-03-03 |  | 100%
3.9 | Sprint retrospektmøte | Andreas | 2024-04-04 | 2024-04-04 |  | 100%
4 | Sprint 3 | ALL | 2024-03-22 | 2024-04-02 |  | 100%
4.1 | Sprint planlegging | Andreas | 2024-03-22 | 2024-03-22 |  | 100%
4.2 | Prototype 3 | Andreas | 2024-03-22 | 2024-03-31 |  | 100%
4.3 | Testplan | Jostein | 2024-03-22 | 2024-03-29 |  | 100%
4.4 | Brukergrensersnitt/Universell Utforming | Jostein | 2024-03-29 | 2024-04-02 |  | 100%
4.5 | Lever Milestone 3 | Jostein | 2024-04-02 | 2024-04-03 | 1 | 100%
4.6 | Sprint gjennomgangsmøte | Andreas | 2024-04-01 | 2024-04-01 |  | 100%
4.7 | Sprint retrospektmøte | Andreas | 2024-04-02 | 2024-04-02 |  | 100%
5 | Sprint 4 | ALL | 2024-04-11 | 2024-04-23 | 12 | 100%
5.1 | Sprint planlegging | Andreas | 2024-04-11 | 2024-04-11 |  | 100%
5.2 | User Case 1-12 | All | 2024-04-11 | 2024-04-22 | 11 | 100%
5.3 | Brukergrensensnitt V2 | Andreas | 2024-04-11 | 2024-04-20 |  | 100%
5.4 | Oppdatere WBS/Gnatt Chart/GitHub | Andreas | 2024-04-21 | 2024-04-21 |  | 100%
5.5 | Presentasjon 2 | Jostein | 2024-04-22 | 2024-04-22 |  | 100%
5.6 | Oppdatere prosjekt status | Jostein | 2024-04-22 | 2024-04-23 | 1 | 100%
5.7 | Sprint gjennomgangsmøte | Andreas | 2024-04-23 | 2024-04-23 |  | 100%
5.8 | Sprint retrospektmøte | Andreas | 2024-04-24 | 2024-04-24 |  | 100%
5.9 | Lever Prosjekt | ALL | 2024-04-25 | 2024-04-25 |  | 100%