## BarkMate
PROJECT TITLE | PRO1000
PROJECT MANAGER | Andreas
COMPANY NAME | BarkMate
DATE | 2024-01-16
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1.0 | Initiation
1.1 | Define Project | Andreas | 2023-03-12 | 2023-03-15 | 3 | 100%
1.2 | Define SWOT | Jostein | 2023-03-15 | 2023-03-21 | 6 | 100%
1.3 | Produkt Backlog | Marcus | 2023-03-16 | 2023-03-22 | 6 | 100%
1.4 | Define Project Criteria | Andreas | 2023-03-17 | 2023-03-22 | 5 | 100%
1.5 | Definere Prosjekt kriterier | Josteim | 2023-03-18 | 2023-03-22 | 4 | 100%
1.2 | Planning
1.2.1 | Develop Project Plan | Jostein | 2024-01-24 | 2024-01-28 | 4 | 90%
1.2.2 | Conduct Marked Reaserch | Marcus | 2024-01-29 | 2024-02-02 | 4 | 100%
1.2.3 | Compile Gantt Chart | Andreas | 2024-02-02 | 2024-02-03 | 1 | 100%
1.2.4 | Submit Milestone 1 | ALL | 2024-02-04 | 2024-02-05 | 1 | 100%
1.2.5 | Project Plan Approved | Marcus | 2024-02-10 | 2024-02-16 | 6 | 80%
1.3 | Excecution
1.3.1 | Project Kickoff Meeting | Marcus | 2024-02-17 | 2024-02-20 | 3 | 100%
1.3.2 | Verify & Validate User Requirements | Andreas | 2024-02-20 | 2024-02-22 | 2 | 80%
1.3.3 | Develop First Prototype | Jostein | 2024-02-22 | 2024-02-24 | 2 | 80%
1.3.4 | Sprint 1 | Andreas | 2024-02-24 | 2024-02-26 | 2 | 60%
1.3.4.1 | Risk Managment | Marcus | 2024-02-27 | 2024-02-29 | 2 | 70%
1.3.4.2 | Submit Milestone 2 | ALL | 2024-03-01 | 2024-03-04 |  | 60%
1.3.4.3 | Develop Second Prototype | Jostein |  |  |  | 0%
1.3.5 | Sprint 2 | Marcus
1.3.9 | Develop Third Protoype | Andreas |  |  |  | 0%
1.3.10 | Testing Phase | Marcus |  |  |  | 0%
1.3.11 | User Training | Andreas |  |  |  | 0%
1.3.12 | Go Live | Jostein |  |  |  | 0%
1.4 | Controll
1.4.1 | Sprint 3 | Andreas |  |  |  | 0%
1.4.1.1 | Project Managment | Marcus |  |  |  | 0%
1.4.1.2 | Update WBS | Andreas |  |  |  | 0%
1.4.1.3 | Update Gantt Chart | Jostein |  |  |  | 0%
1.4.1.4 | Update GitHub | Andreas |  |  |  | 0%
1.4.1.5 | Excecute and Document Sprint | Marcus |  |  |  | 0%
1.4.2 | Sprint 4 | Andreas |  |  |  | 0%
1.4.3 | Project Status Meeting | Jostein |  |  |  | 0%
1.5 | Closeout
1.5.1 | Submit Milestone 3 | ALL |  | 2024-04-01 |  | 0%
1.5.2 | Evaluation Meeting | Jostein |  |  |  | 0%
1.5.3 | Document Lessions Learnt | Andreas |  |  |  | 0%
1.5.4 | Create Plan for Next Step | Marcus |  |  |  | 0%
1.5.5 | Archive Files | Jostein |  |  |  | 0%
1.5.6 | Close Project | ALL |  | 2024-04-24 |  | 0%