## BarkMate
PROJECT TITLE | PRO1000
PROJECT MANAGER | Andreas
COMPANY NAME | BarkMate
DATE | 2024-01-16
[6 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | COMPLETE | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1.1 | Start
1.1.1 | Definere Prosjekt | Andreas | 2023-03-12 | 2023-03-15 | 100%
1.1.2 | Definere SWOT | Jostein | 2023-03-15 | 2023-03-21 | 100%
1.1.3 | Produkt Backlog | Marcus | 2023-03-16 | 2023-03-22 | 100%
1.1.4 | Definere Prosjekt | Andreas | 2023-03-17 | 2023-03-22 | 100%
1.2 | Planlegging
1.2.1 | Bygge opp prosjektplan | Jostein | 2024-01-24 | 2024-01-28 | 90%
1.2.2 | Markedsundersøkelser | Marcus | 2024-01-29 | 2024-02-02 | 100%
1.2.3 | Estimere Gnatt Chatt | Andreas | 2024-02-02 | 2024-02-03 | 100%
1.2.4 | Levere Milestone 1 | ALL | 2024-02-04 | 2024-02-05 | 100%
1.3 | Utførelse
1.3.1 | Sprint 1 | Marcus | 2024-02-12 | 2024-03-04 | 100%
1.3.2 | Validere brukergrensesnittet | Andreas | 2024-02-23 | 2024-02-18 | 100%
1.3.3 | Prototyppe 1 | Jostein | 2024-02-27 | 2024-02-24 | 100%
1.3.4 | Risikovurdering | Andreas | 2024-02-28 | 2024-02-26 | 100%
1.3.5 | Levere Milestone 2 | Marcus | 2024-02-29 | 2024-02-29 | 100%
1.3.6 | Prototype 2 | ALL | 2024-03-01 | 2024-03-04 | 60%
1.3.7 | Sprint 2 | Jostein | Uke 7 | Uke 8 | 0%
1.3.8 | Prototype 3 | Marcus | Uke 7 | Uke 8 | 0%
1.3.9 | Test fase | Andreas | Uke 7 | Uke 8 | 0%
1.3.10 | Brukergrensersnitt/Universell Utforming | Marcus | Uke 7 | Uke 8 | 0%
1.3.11 | Go Live | Jostein | Uke 7 | Uke 8 | 0%
1.4 | Controll
1.4.1 | Sprint 3 | Andreas | Uke 8 | Uke 9 | 0%
1.4.2 | Prosjekt Ovesikt | Marcus | Uke 8 | Uke 9 | 0%
1.4.3 | Oppdatere WBS/Gnatt Chart/GitHub | Andreas | Uke 8 | Uke 9 | 0%
1.4.4 | Prosjekt status orientering | Andreas | Uke 8 | Uke 9 | 0%
1.4.5 | Oppdatere prosjekt status | Jostein | Uke 8 | Uke 9 | 0%
1.5 | Sluttprosess
1.5.1 | Sprint 4 | ALL | Uke 10 | Uke 13 | 0%
1.5.2 | Lever Milestone 3 | Jostein | Uke 10 | Uke 13 | 0%
1.5.3 | Evaluerings Møte | Andreas | Uke 10 | Uke 13 | 0%
1.5.4 | Dokoumentasjon for læring | Marcus | Uke 10 | Uke 13 | 0%
1.5.5 | Arkivere filer | Jostein | Uke 10 | Uke 13 | 0%
1.5.6 | Lever Prosjekt | ALL |  | 2024-04-24 | 0%